## Overview
Optimo — Project Management Plan
Recipe Database Manager · Streamlit app · CA DIAT
Author | Afagh Dashti (Data Analyst — CA analysis team)
Team | CA DIAT + stakeholders (Menu Planning / POA / iPPA)
Repo | ~/Documents/GitHub/ca-datalit/webapp/staging/optimo/
Branch | App/Staging/CDIA-2858/Optimo_Analytics_Tab_v2
Live tracker | ~/Claude/Projects/Optimo/optimo_pm_tracker.html (interactive Gantt)
Last updated | 2026-07-28
How to use this tracker
1. Tasks grouped by page/tab of Optimo. Within each group: Done → Pending Eng Review → In progress → Not started → Backlog.
2. Priority is High / Medium / Low. Status is Done / Pending Engineering Review / In progress / Not started / Backlog / Blocked / Cancelled — colour-coded.
3. Stakeholder = person who requested it. Category = one of 5 buckets used by the interactive Gantt (only for open work).
4. Start + Target dates drive the Gantt in the HTML tracker. Both required for a bar to appear.
5. Metrics sheet rolls up counts automatically.
6. Save as xlsx or upload to Google Sheets — filters and conditional formatting carry over.
Legend
Status | Done · Pending Engineering Review · In progress · Not started · Backlog · Blocked · Cancelled
Priority | High · Medium · Low
Pages | Menu Analytics · Menu Validation · Menu Architecture · Recipe Pool · Data Validation · Infra / Deployment · Docs
Categories | Data & Logic Accuracy · New Filters & Controls · New Views & Information · Redesigns & New Capabilities · Deployment & Refactoring
Sources | PR #1162 (merged) · PR #1173 (pending Eng review) · Feedback tracker · Jira tickets · Bigger-changes list

## Milestones
Milestones & category rollup
Shipped PRs first, then open-work categories. Task-level tracking is on the Tasks sheet.
Milestone / Category | Start | End | Status | # tasks | Description
Menu Analytics — CP + HF Final (PR #1173) | 2026-07-14 | 2026-08-15 | Pending Engineering Review |  | Chef's Plate + HF Final menu, EDW backfill to 2024-W01, Tab 7 swap detection, New Recipes count fix + list.
Data & Logic Accuracy | 2026-07-28 | 2026-12-11 | Not started | 7 | MA-12, MA-14, MV-09, MAR-01, RP-01, RP-02, RP-03
New Filters & Controls | 2026-08-20 | 2026-11-12 | Not started | 4 | MA-11, MV-02, MV-03, MV-08
New Views & Information | 2026-09-01 | 2026-11-08 | Not started | 4 | MA-15, MA-16, MV-01, MV-05
Redesigns & New Capabilities | 2026-09-05 | 2027-02-21 | Not started | 3 | MA-17, MV-06, MV-07
Deployment & Refactoring | unscheduled | unscheduled | Not started | 2 | DV-01, INF-01

## Tasks
Tasks
Grouped by Optimo page/tab. Done items first, then Pending Eng Review, In progress, Not started, Backlog.
ID | Task | Priority | Status | Stakeholder | Start | Target | Notes | Category
Menu Analytics
MA-01 | Build initial Menu Analytics page — tabs, charts, and sign-off scorecard; wire into Optimo staging navigation | High | Done |  |  |  | PR #1162 (merged)
MA-02 | Add Photon/Snowflake SQL queries and data_fetcher helpers (demand, popularity, performance, seasonality, trend) to power RIS/RAR/AOR | High | Done |  |  |  | PR #1162 (merged)
MA-03 | Author DASHBOARD_MANUAL.md (metric lineage documentation) | Medium | Done |  |  |  | PR #1162 (merged)
MA-04 | Add page-specific styling (analytics_style.css) | Low | Done |  |  |  | PR #1162 (merged)
MA-13 | Review New Recipe logic — count was displaying values in the 20s | Low | Done | Emma Szalai |  |  | Feedback tracker. Fixed as part of PR #1173.
MA-05 | Add Chef's Plate final menu to Menu Analytics page | High | Pending Engineering Review | Karren |  |  | PR #1173
MA-06 | Add HelloFresh Final menu to Menu Analytics page | High | Pending Engineering Review | Linnea |  |  | PR #1173
MA-07 | Backfill EDW final-menu data to 2024-W01 | Medium | Pending Engineering Review | Linnea |  |  | PR #1173
MA-08 | Tab 7 — add GAMP ↔ Final swap detection | Medium | Pending Engineering Review | Emma |  |  | PR #1173
MA-09 | Composition tab — fix New Recipe count for GAMP and Final versions | Medium | Pending Engineering Review |  |  |  | PR #1173
MA-10 | Composition tab — add New Recipes list | Medium | Pending Engineering Review | Emma |  |  | PR #1173
MA-11 | Add Recipe Type filter (surcharge, core, etc.) to Menu Analytics | High | Not started | Linnea | 2026-08-20 | 2026-08-25 | Jira ticket. Discuss with Irene. | New Filters & Controls
MA-12 | Investigate preference-value source in codebase and correct the Preference filter values | High | Not started |  | 2026-10-17 | 2026-10-25 | Jira ticket. Companion to MAR-01. | Data & Logic Accuracy
MA-14 | Update low-score threshold (move from 4-point rating to 5) after confirming target with Tim G. | Low | Not started | Emma Szalai | 2026-08-26 | 2026-08-31 | Feedback tracker — dependency: confirm new threshold with Timothy Guo | Data & Logic Accuracy
MA-15 | Expose recipe titles inline alongside Menu Analytics charts (gut-check titles from the protein mix and other charts) | Low | Not started | Emma Szalai | 2026-10-13 | 2026-10-16 | Feedback tracker | New Views & Information
MA-16 | Protein mix chart — break out into specific protein cuts within groups (e.g. sub-buckets under Chicken) | Medium | Not started | Emma Szalai | 2026-09-01 | 2026-09-04 | Feedback tracker | New Views & Information
MA-17 | AI-based recommendations for Recipe Swaps and Menu Optimisation | Medium | Backlog |  | 2026-12-12 | 2027-02-21 | Bigger change | Redesigns & New Capabilities
Menu Validation
MV-04 | Final Menu — surface the most-up-to-date version (pull from MPS directly, not just initial GAMP upload) | High | Done | Emma Szalai |  |  | Feedback tracker. Landed with the PR #1173 Final-menu integration.
MV-01 | Menu Review — Ineligible Recipes should display protein / preference / tag assignments, with an in-tab way to update them | Medium | Not started | Emma Szalai | 2026-10-26 | 2026-11-08 | Feedback tracker | New Views & Information
MV-02 | Recipe Shortlist — add a way to filter recipes within a swap (currently a 2000+ list; workaround is ctrl-F) | Medium | Not started | Emma Szalai | 2026-09-23 | 2026-09-30 | Feedback tracker | New Filters & Controls
MV-03 | Final Menu view — make it filterable by slot architecture (currently only slot-number search) | Medium | Not started | Emma Szalai | 2026-10-05 | 2026-10-12 | Feedback tracker | New Filters & Controls
MV-05 | Menu Review — add a summary dashboard inside the tab | Medium | Not started |  | 2026-10-01 | 2026-10-04 | Bigger change | New Views & Information
MV-06 | Redesign the Swap function in Optimo | High | Not started |  | 2026-09-05 | 2026-09-13 | Bigger change — pair with MV-07 | Redesigns & New Capabilities
MV-07 | Implement the new design for Swap | High | Not started |  | 2026-09-14 | 2026-09-22 | Bigger change — follows MV-06 | Redesigns & New Capabilities
MV-08 | Menu Upload — searchable columns not bound by the strict uploading-menu rule | Medium | Not started | Timothy Guo | 2026-11-09 | 2026-11-12 | Feedback tracker — current workaround: manually adjust the column | New Filters & Controls
MV-09 | Funnel GAMP constraints into Optimo so Menu Analytics can show easy sign-off checks (e.g. balanced meals hit 20%) | High | Not started | Emma Szalai | 2026-11-13 | 2026-12-11 | Feedback tracker — replaces ad-hoc menu sign-off checks. Includes investigation + scoping. | Data & Logic Accuracy
Menu Architecture
MAR-01 | Correct preference values in Menu Architecture to match personalization values | High | Not started |  | 2026-07-28 | 2026-08-05 | Bigger change. Companion to MA-12. | Data & Logic Accuracy
Recipe Pool
RP-01 | Correct Total_Time column in Recipe Pool | Medium | Not started | Irene | 2026-08-06 | 2026-08-09 | Jira: Recipe_Pool_Table_Optimisation | Data & Logic Accuracy
RP-02 | Correct Cost2p column after revising it in Recipe Pool | Medium | Not started | Irene | 2026-08-10 | 2026-08-13 | Jira: Recipe_Pool_Table_Optimisation | Data & Logic Accuracy
RP-03 | Optimize recipe_pool_master_enriched query | Medium | Not started |  | 2026-08-14 | 2026-08-19 | Query/pipeline optimization — foundation for downstream Recipe Pool work | Data & Logic Accuracy
Data Validation
DV-01 | Remove the Data Validation tab or fold its code into another page | Medium | Not started |  |  |  | Bigger change — decision needed | Deployment & Refactoring
Infra / Deployment
INF-01 | Discuss and agree on the process for pushing updates from Optimo Staging to Optimo Live | High | Not started |  |  |  | Bigger change — release process. TBD pending decision. | Deployment & Refactoring

## Metrics
Status rollups
Computed live from the Tasks sheet — do not edit.
By status
Status | Count
Done
Pending Engineering Review
In progress
Not started
Backlog
Blocked
Cancelled
By page
Page | Total | Done | Pending Eng | In progress | Not started
Menu Analytics | 17 | 5 | 6 | 0 | 5
Menu Validation | 9 | 1 | 0 | 0 | 8
Menu Architecture | 1 | 0 | 0 | 0 | 1
Recipe Pool | 3 | 0 | 0 | 0 | 3
Data Validation | 1 | 0 | 0 | 0 | 1
Infra / Deployment | 1 | 0 | 0 | 0 | 1
By priority
Priority | Total
High
Medium
Low
By category
Category | Total
Data & Logic Accuracy
New Filters & Controls
New Views & Information
Redesigns & New Capabilities
Deployment & Refactoring
Totals
Total tasks | 32
% done